## Combined
Project Name | Zone | High Priority - Agency noted | (mapped) | Public/Stakeholder Support | Status (select from dropdown menu) | Project Description | Project Type | Property Name | Agency | CIP (if yes, date/list) | Planning Document | Other Agencies to Coordinate With | Construction Cost | Amount Funded | Funding Source(s) for Funded Amount | Amount Unfunded | Potential Funding Sources for Unfunded Amount | Time Horizons | Goal 1: Regional Planning and Partnerships | Goal 2: Vegetation Management | Goal 3: Plant and Animal Habitat Conservation and Restoration | Goal 4: Historic, Cultural, and Archaeological Resources | Goal 5: Public Safety | Goal 6: Public Access and Regional Connections | Goal 7: Stewardship, Maintenance, and Facilities
Restroom at Four Mile Beach | No Zone |  |  |  | Potential | May be challenging location, added due to lack of restroom | Visitor Facilities | Four Mile Beach | California State Parks
Trash Receptacles at Four Mile Beach | No Zone |  |  |  | Potential | Added due to lack of trash receptacles | Visitor Facilities | Four Mile Beach | California State Parks
Four Mile Beach Parking Lot | No Zone | x | Y | x | Planned - 20 yrs | Parking lot at Four Mile Beach | Parking | Four Mile Beach | California State Parks | CSP Priority List | [13 empty] | x
Parking at Shark Fin Cove | No Zone |  |  |  | Potential | Adequate parking requested in survey | Parking
Trash Receptacles at Shark Fin Cove | No Zone |  |  |  | Potential | Added due to lack of trash receptacles | Visitor Facilities
Restroom at Shark Fin Cove | No Zone |  |  |  | Potential | May be challenging location, added due to lack of restroom | Visitor Facilities
MBSST Segment 1 | Zone 1: Big Basin | x | Y | x | On hold - pursue funding | Segment 1 proposed improvements include: • 0.87 miles (4,600 LF) Class III on-street/road shoulder bike route • 0.19 miles (1,000 LF) unpaved native soil trail • Unpaved roadway shoulder on coastal side of Highway 1 • Fencing may be considered when project is implemented | Trails | North Coast Rail Trail/Highway 1 | RTC | RTC Priority List | MBSST Master Plan; Santa Cruz County ATP | State Parks | 107120-needs to be updated | no | na | x | Private Partners, Land Trust, grants | NA | x |  |  |  | x | x | x
Trail Loop | Zone 1: Big Basin |  | n |  | Planned - 20 yrs | Pursue Regional Overnight multi-use trail loop | Trails | Big Basin Redwoods SP | California State Parks | n/a | Reimagining Big Basin - Conceptual Priorities | [12 empty] | x
CCT Connections | Zone 1: Big Basin | x | Y |  | Planned - 20 yrs | Pursue connections to California Coastal Trail | Trails | Big Basin Redwoods SP | California State Parks | n/a | Reimagining Big Basin - Conceptual Priorities | [12 empty] | x
RDO Upgrades | Zone 1: Big Basin | x | Y |  | Planned - 20 yrs | Rancho Del Oso Upgrades | Visitor Facilities | Big Basin Redwoods SP | California State Parks | n/a | Reimagining Big Basin - Conceptual Priorities | [12 empty] | x | x
Waddell Beach Parking | Zone 1: Big Basin |  | Y |  | Planned - 20 yrs | Coordinate with Caltrans to maintain and expand Waddell Beach parking facilities, as feasible, to support beach activities and ocean view parking. | Parking | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | Caltrans | [11 empty] | x
Highway Improvements | Zone 1: Big Basin |  | Y |  | Planned - 20 yrs | Improve highway signage and implement effective measures to slow vehicle traffic and provide early warning to motorists for approaching intersection and pedestrian crossing. | Highway | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | Caltrans | [10 empty] | x | x
Day Use Parking and Pedestrian Highway Safety | Zone 1: Big Basin |  | Y |  | Planned - 20 yrs | As part of a fully integrated plan for both sides of the highway, incorporate day use parking (50 -100 spaces), distributed on either side of Highway 1 depending on resource constraints and future roadway alignment, with safe pedestrian access from the inland side of the highway to Waddell Beach. | Parking | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [11 empty] | x | x
Roadside Habitat Monitoring and Protection | Zone 1: Big Basin |  | n |  | Planned - 20 yrs | Protect special status plant and wildlife habitats, conduct resource surveys and monitor use along roadways and near sensitive habitats, and implement resource management and protective measures to eliminate or mitigate human impacts on significant natural resources. | Habitat | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [8 empty] | x | x
Horse Camp Upgrades | Zone 1: Big Basin |  | Y |  | Planned - 20 yrs | Upgrade or reconfigure the horse camp and equestrian staging facilities to improve campsites, trailer parking and vehicle circulation. | Campground | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [12 empty] | x | x
Resource Surveys and Site Plans | Zone 1: Big Basin |  | n |  | Planned - 20 yrs | Conduct additional site-specific surveys, as necessary, to identify natural and cultural resource sensitivities and protective measures, and prepare site plan(s) to determine the location, size, and configuration of desired public use and park operations facilities. | Planning | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [9 empty] | x | x |  |  | x
Visitor Experience Upgrades | Zone 1: Big Basin |  | n |  | Planned - 20 yrs | Address public health and safety issues, accessibility requirements, aesthetics, interpretation, and management of visitor capacity. | Visitor Facilities | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [12 empty] | x | x
Bicycle Camp | Zone 1: Big Basin |  | Y |  | Planned - 20 yrs | Develop a bicycle camp and walk-in campground facilities at a location either adjacent to the horse camp or in an open area along the existing road north of the day use parking lot. Consider alternative forms of camp facilities, such as yurts or tent cabins, with provisions to serve backpackers and touring bicyclists utilizing the California Coastal Trail (CCT) and Highway 1 Pacific Coast Bike Route (PCBR). | Campground | Big Basin Redwoods SP | California State Parks | n/a | Big Basin Redwoods GP | [12 empty] | x | x
Greyhound Rock Beach Improvements | Zone 2: Greyhound Rock |  | Y |  | Planned - 10 yrs | institute fees for the parking lot, permit overnight use by up to 25 RVs per night (requires variance from LCP) | Parking | Greyhound Rock Beach | Santa Cruz County | n/a | North Coast Beaches Master Plan, Appendix II | It is difficult to charge for parking w/ CCC wanting free coastal access. Park is technically closed overnight, but we'd like to create a permitted overnight parking/camping program in the future. | [11 empty] | x
Restroom at Scott Creek | Zone 3: Scott Creek |  |  |  | Potential | May be challenging location, added due to lack of restroom | Visitor Facilities
Parking at Scott Creek | Zone 3: Scott Creek |  |  |  | Potential | May be challenging location, added due to lack of parking | Parking
Scotts Creek Coastal Resiliency Project | Zone 3: Scott Creek |  | Y | x | Planned - 10 yrs | On State Route 1 from Postmile 31.28 to 31.96. The Scott Creek Lagoon Restoration Project proposes to replace the existing Scott Creek Bridge (Br No. 36 0031) with an 800 foot bridge that addresses the needs of the proposed restoration of the Scott Creek Lagoon. PID document is a Project Study Report-Project Development Support (PSR-PDS) and was completed in October 2021. Design information is pulled from the Scott Creek Lagoon and Marsh Restoration Project 60% Engineering Design Plans and Basis of Design Report that was funded by the Resources Conservation District of Santa Cruz County. Funding for envirnemental review, final Design, and construction has not yet been secured. | Infrastructure, Conservation |  | Collaboration: Caltrans, SCCRTC, Resources Conservation District of Santa Cruz County (RCD) |  | Caltrans SCC Biannual SHOPP Packet, 08/2022; SCCRTC's 2045 Regional Transportation Plan Appendix E Project List as ID: CT34 or search EA 05-1M720. | California Department of Fish and Wildlife, Wildlife Conservation Board, California Coastal Conservancy, US Fish and Wildlife Service Coastal Program, and NOAA Fisheries | 100000000 | 3530000 | IIJA Protect through Caltrans' SHOPP | 96470000 | IIJA PROTECT funds through Caltrans' SHOPP | Target RTL is currently listed for FY 2028/29 | Yes- Multi-agency effort to improve a habitat area, the State Highway System, and coastal facilities. Complete Street features encourage regional recreation and is in line with Caltrans' multi-modal goals. | Yes- Goes hand-in-hand with Lagoon Restoration | Yes- Lagoon restoration |  | Yes- Adds off-street parking facilities where both formal and informal on-street parking currently occurs. Proposed Design features include Complete Streets-bike & pedestrian elements | Yes- Moves existing on-street parking to off-street and adds additional off-street parking facilities for beach access | Yes- Adds parking lot and improves the bridge structure by replacing it
MBSST Segment 3 | Zone 3: Scott Creek | x | Y | x | On hold - pursue funding | Segment 3 proposed improvements include: • 1.11 miles (5,870 LF) multi-use paved path (Class I) • One (1) preengineered bike/pedestrian bridge, one-hundred-and-fifty- (150-) foot span • Fencing may be considered when project is implemented | Trails | North Coast Rail Trail | RTC | RTC Priority List | MBSST Master Plan | State Parks | 2550096- needs to be updated | no | na | x | Private Partners, Land Trust, grants | NA | x |  |  |  | x | x | x
MBSST Segment 2 | Zone 3: Scott Creek; Zone 2: Greyhound Rock Zone | x | Y | x | On hold - pursue funding | Segment 2 proposed improvements include: • 4.77 miles of primarily existing road shoulder improvements due to limited available space and adjacent public land on the coastal side of State Highway 1 • Routine road edge clearing, signs, and shoulder pavement striping • Fencing may be considered when project is implemented | Trails | North Coast Rail Trail/Highway 1 | RTC | RTC Priority List | MBSST Master Plan | State Parks | 308032-needs to be updated | no | na | x | Private Partners, Land Trust, grants | NA | x |  |  |  | x | x | x
MBSST Segment 4 | Zone 4: Davenport | x | Y | x | On hold - pursue funding | Segment 4 proposed improvements include: • 1.38 miles (7,300 LF) multi-use rail trail (Class I) • 1.41 miles (7,470 LF) bluff trail (Segment 4A) • 0.85 miles (4,510 LF) on-street bike lanes (Segment 4B) • One (1) Highway 1 crossing at Davenport Landing Road • One (1) rail crossing in front of cement plant • Three (3) road crossings • Fencing may be considered when project is implemented | Trails | North Coast Rail Trail/Santa Cruz Branch Rail Line | RTC | RTC Priority List | MBSST Master Plan | State Parks | 2685424-needs to be updated | no | na | x | Private Partners, Land Trust, grants | NA | x |  |  |  | x | x | x
Davenport Landing Beach Access and Aesthetic Improvements | Zone 4: Davenport |  | Y | x | Planned - 10 yrs | widen and pave Title 24 trail with landing and <8% slope, restructure Davenport Landing roadway for paid parking on inland side with one-way movement and “no parking” signs on coastal side of road and railing along creek outfall and downhill side of trail, restructure hillside to create adequate sight distance for cars exiting parking area and “no turning” signs both directions on Highway 1, consider permit parking in front of existing residences, restrooms along trail and visually screen from residences. | Trails | Davenport Landing | Santa Cruz County | n/a | North Coast Beaches Master Plan, Appendix II | *This is partially completed, but the road improvements were not done and need to be coordinated with County DPW. | [11 empty] | x
EIR Adjustment 10 | Zone 4: Davenport |  | Y | x | Planned - 5 yrs | The improvement of the Davenport Landing Road/Highway 1 intersection. | Highway | Davenport Landing | Santa Cruz County | n/a | North Coast Beaches Master Plan, Appendix III DEIR | Discuss with the WG (DPW and Caltrans) to understand more about what is proposed here. Turning lane? I’m unfamiliar with the problem that needs to be addressed, and since it is Hwy 1 that would need modifying, Caltrans will have the final say. One thing that just came to mind is that this should probably be combined with improvements to Hwy 1 to accommodate an entrance to Cotoni-Coast Dairies across the street on Cement Plant Road. So please put this at the 5-year horizon unless Caltrans or BLM has plans to improve that intersection already, which they might. | [10 empty] | x
RMZ 1 Trails (PHASE 1) | Zone 4: Davenport |  | Y | x | Underway/Imminent | for hiking and bicycling: 7.73 mi and 6.29 mi, phased | Trails | Cotoni-Coast Dairies | BLM | n/a | Decision Record for CCNM RMP Amendment for C-CD | California Coastal Commission, County Public Works | $3.2M | $2M | Santa Cruz Mountain Trail Stewardship | $1.2M | Donation | 1yr | x |  |  |  |  | x | x
Historic Feature Preservation and Restoration | Zone 4: Davenport | x | Y | x | Planned - 5 yrs | Preserve and restore the Mocettini Cheese Barn and the other historic features nearby | Historic Preservation | Cotoni-Coast Dairies | BLM | BLM Priority List | https://eplanning.blm.gov/eplanning-ui/project/2022460/510 | California Coastal Commission, Office of Historic Preservation, National Parks Service, California State Parks | TBD | TBD | TBD | TBD | TBD | TBD |  |  |  | x | x |  | x
Parking for Northern Trailhead (= Surrogate for Warrenella Road Gate Parking Lot - on hold). | Zone 4: Davenport | x | Y | x | Planned - 5 yrs | Parking near Warranella Road and Cement Plant Road | Parking | Cotoni-Coast Dairies | BLM | BLM Priority List | https://eplanning.blm.gov/eplanning-ui/project/2021942/510 | California Coastal Commission, Santa Cruz County, County Public Works, CALTRANS | TBD | TBD | TBD | TBD | TBD | 2yr | x |  |  |  | x | x | x
Warranella Road Fuelbreak Maintenance | Zone 4: Davenport | x | Y | x | Planned - 5 yrs | Maintain the Warrenella Road Fuelbreak in conjunction with San Vicente Redwoods effort | Vegetation Management | Cotoni-Coast Dairies | BLM | BLM Priority List | Decision Record for CCNM RMP Amendment for C-CD | CALFIRE, Santa Cruz Fire Safety Council | TBD | TBD | TBD | TBD | TBD | TBD | x | x | x |  | x | x | x
Davenport Bluffs and Beach Access Improvements and Restoration | Zone 4: Davenport |  | Y |  |  | Develop 26-vehicle paid lot with combined entrance/exit near center of site with guard rail separating lot from highway and low-growing native shrubbery around, develop 14-vehicle non-paid lot (separate entrance/exit) farther west by railroad crossings with low-growing native shrubbery around, extend existing center turning lane to reach 26-vehicle lot, deceleration and acceleration lanes to both lots, provide stairs with handrails to main beach area and on railroad embankments between 14-vehicle lot and cypress bluffs, restrooms screened with native plants near 26-vehicle lot, fencing along top of bluffs and at all unimproved trailheads and to preserve Rhinoceros Auklet, Pigeon Guillemot, and Black Swift nesting areas and to control access to railroad tracks, add warning signs and devices required by southern Pacific Railroad Company. | Parking | Davenport Bluffs and Beach |  | n/a | North Coast Beaches Master Plan, Appendix II | RTC plans to construct a parking lot at Davenport on the coast side of Highway 1. The proposed project provides formal free parking, restrooms, and connection from parking lot to the Coastal Rail Trail on the coast side of the tracks between Davenport and Wilder Ranch. It does not include non- Coastal Rail Trail trail improvements, bluff top improvements, improvements targeted to improve bird nesting areas, rail crossing improvements, or planting shrubbery. | [8 empty] | x |  |  | x
Davenport Bluffs and Beach (UP: Access and Restoration) | Zone 4: Davenport |  | Y |  |  | Highway 1 turning lanes, guard rail, and bus stop; 2 parking lots and fee boxes; concrete stairs with handrails; emergency telephone; trash cans; vault toilets; beach clean-up; signs; vegetation restoration and wildlife protection; and concrete rail safety fencing | Parking | Davenport Bluffs and Beach | Caltrans | n/a | North Coast Beaches Unified Plan | [9 empty] | x |  |  | x
CEMEX Property Shared Use Path | Zone 4: Davenport |  | Y |  |  | Study options to construct shared use path through CEMEX property to connect New Town with Marine View Ave, as outlined in CEMEX reuse plan (private property) | Trails | CEMEX Property | Private | n/a | Santa Cruz County ATP | [11 empty] | x | x
Cement Plant Road Multi-Use Path | Zone 4: Davenport |  | Y | x |  | Conduct feasibility study to install Class I multi-use path on Cement Plant Rd (Davenport) | Trails | CEMEX Property/ Davenport CDP | Private | n/a | Santa Cruz County ATP | [12 empty] | x
CEMEX Redevelopment | Zone 4: Davenport |  |  |  | Planned - 20 yrs
Bonny Doon Beach Access Improvements | Zone 5: Bonny Doon Beach | x | Y |  | Planned - 5 yrs | Public access improvement to Bonny Doon beach with a link to the rail trail | Trails | Bonny Doon Beach | California State Parks | CSP Priority List | [13 empty] | x
Bonny Doon Beach Improvements and Restoration | Zone 5: Bonny Doon Beach |  | Y |  | Planned - 20 yrs | Highway 1 turning lanes, guard rail, culvert extension, bus stop; paved parking area and fee boxes; concrete stairs with handrails and wood stairs with handrails; trans cans; vault toilets; emergency phone; beach clean-up; signs; dune and coastal scrub restoration and preservation | Visitor Facilities | Bonny Doon Beach | California State Parks | n/a | North Coast Beaches Unified Plan | [9 empty] | x |  |  | x
RMZ 3 Trails (PHASE 1) | Zone 6: Yellowbank/Panther Beach |  | Y | x | Planned - 5 yrs | for hiking and equestrian: 5.16 mi and 2.79 mi, phased. For hiking, bicycling, equestrian: 4.61 mi | Trails | Cotoni-Coast Dairies | BLM | n/a | Decision Record for CCNM RMP Amendment for C-CD | California Coastal Commission, California State Parks, Regional Transportation Commission | $2M | 0 | TBD | $2M | Grant | 3yr | x |  |  |  |  | x | x
Parking for Southern Trailhead | Zone 6: Yellowbank/Panther Beach |  | TBD | x | Planned - 5 yrs | Pursue opportunities to establish a parking lot (day use site) on or adjacent to the BLM public lands to provide public access to RMZ 3. | Parking | Cotoni-Coast Dairies | BLM | n/a | TBD | California Coastal Commission, California State Parks, Regional Transportation Commission, CALTRANS, County of Santa Cruz | TBD | TBD | TBD | TBD | TBD | TBD | x |  |  |  | x | x | x
Bike/Ped Hwy 1 Overcrossing at Yellowbank | Zone 6: Yellowbank/Panther Beach | x | Y |  | Planned - 5 yrs | North Coast Rail Trail and Yellowbank/Panther Beach pedestrian and bicycle overcrossing of Hwy 1 (pending grant award) | Trails | North Coast Rail Trail | RTC | RTC Priority List | MBSST Master Plan | FHWA-CFL/ Cotoni Coast Dairies | approximate $3M, updated cost coming soon | Yes | Federal Lands Access program | fully funded |  | Construction in 2026 if funding is secured | X |  |  | x | x | x | x
Panther Beach Access Improvements | Zone 6: Yellowbank/Panther Beach | x | Y | x | Planned - 5 yrs | Public access improvement to Panther Beach from the top of the bluff | Trails | Panther Beach | California State Parks | CSP Priority List | [13 empty] | x
Panther Beach (GP: Access) | Zone 6: Yellowbank/Panther Beach |  | Y |  | Planned - 20 yrs | guard rail between highway edge and existing parking area, with opening at the south end for ingress and egress and providing space for 30 vehicles, parking fee envelope dispensing and repository boxes near lot entrance, concrete stairs with a pipe handrail down to the beach with landings where possible, trash containers at the beach and trailhead, a vault toilet at the trailhead, or at the top of the stairs where it would be accessible by farm road, signs. | Visitor Facilities | Panther Beach | California State Parks | n/a | General Plan for the North Coast Beaches | [12 empty] | x
Panther Beach Amenities | Zone 6: Yellowbank/Panther Beach |  | Y |  | Planned - 20 yrs | concrete stairs with handrail, trash cans, signs | Visitor Facilities | Panther Beach | California State Parks | n/a | North Coast Beaches Unified Plan | [12 empty] | x
Yellowbank Beach Access Improvements and Restoration | Zone 6: Yellowbank/Panther Beach |  | Y | x | Planned - 20 yrs | Highway 1 turning lanes and bus stop; parking lot with guard rail, fee boxes, and relocation of electrical poles; concrete stairs with handrail; trash cans; vault toilets; beach clean-up; emergency telephone; signs; and coastal scrub revegetation | Visitor Facilities | Yellowbank Beach | California State Parks | n/a | North Coast Beaches Unified Plan | [9 empty] | x |  |  | x
Overpass at Panther Gap | Zone 6: Yellowbank/Panther Beach | x | Y | x | Planned - 5 yrs | Overpass to connect NCRT at Panther Gap to the C-CD near Yellow Bank Creek | Trails | Cotoni-Coast Dairies | BLM | BLM Priority List | Federal Highway Administration (FHWA) is project lead. | Federal Highway Administration, Regional Transportation Commission, CALTRANS, County of Santa Cruz, California Coastal Commission, California State Parks | TBD | TBD | TBD | TBD | TBD | 3yr | x |  |  |  | x | x | x
Potable Water Supply to Panther or BLM Lot | Zone 6: Yellowbank/Panther Beach |  |  | x | Potential
Yellowbank Trailhead | Zone 6: Yellowbank/Panther Beach |  |  | x | Potential | plans for parking lot put forth by FONC in stakeholder interview, plans have been sent to TPL (landowner)
Laguna Creek Beach (GP: Access and Preserve) | Zone 7: Laguna Creek + C-CD |  | Y |  | Planned - 20 yrs | add paved shoulders for turning onto Laguna Creek Road to parking lot, paint pedestrian crossing zone on highway surface between trailhead and opening in parking lot guard rail, guard rail between roadway edges and parking area with openings near the rear for ingress and egress, gate and tire teeth, entrance kiosk, parking fee envelope dispensing and repository boxes, widen access trail section between railroad track and highway, grade farm road evenly for pump truck access, concrete stairs with pipe handrail down coastal bluff to pocket beach at north end, trail barriers at either end of secondary trail along wetland, trash containers, vault toilets along the trail on the lower beach or at the rear of the parking lot, signs, establish wetland preserve, protect snowy plover nesting area. | Highway | Laguna Creek Beach | California State Parks | n/a | General Plan for the North Coast Beaches | [9 empty] | x |  |  | x
Laguna Creek Beach Marsh Preservation | Zone 7: Laguna Creek + C-CD |  | Y |  | Planned - 20 yrs | beach clean-up, marsh/Snowy Plover preservation | Habitat | Laguna Creek Beach | California State Parks | n/a | North Coast Beaches Unified Plan | [9 empty] | x
Old Cove Landing Trail Accessibility Improvements | Zone 8: Wilder Ranch | x | Y | x | Planned - 5 yrs | Make the Old Cove Landing trail at Wilder ADA accessible | Trails | Wilder Ranch SP | California State Parks | CSP Priority List | [13 empty] | x
Wilder Ranch Cultural Preserve | Zone 8: Wilder Ranch | x | Y |  | Planned - 5 yrs | Wilder Ranch Complex renovate Bolcoff Adobe and Grainery | Cultural Preserve | Wilder Ranch SP | California State Parks | CSP Priority List | Wilder Ranch SP General Plan, 1980 | [10 empty] | x
Note on F35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Carie (LTSCC) heard from Semperviren’s Fund that a group of stakeholders worked on this for years, but there are no plans at this time. Keep?
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Carie (LTSCC) heard from Semperviren’s Fund that a group of stakeholders worked on this for years, but there are no plans at this time. Keep?

## DropdownRef
Completed
Underway/Imminent
Planned - 5 yrs
Planned - 10 yrs
Planned - 20 yrs
Canceled/On hold
On hold - pursue funding